Donora+

Development Plan

Practical roadmap from project setup to tested MVP deployment

Basis: Donora+ Product Requirements Document (Version 1.0, August 2026) and the previously prepared System Architecture Document. The PRD defines a three-person team, a hackathon-focused MVP, and a deliberately minimal six-day build strategy. The plan below converts those requirements into executable development work.

# 1. Development Objective

The primary objective is not to build every future Donora+ feature. It is to produce a stable, demoable, end-to-end MVP in which a donor can register and become verified, a seeker can create a blood request, compatible eligible donors can be discovered on a map, both parties can initiate chat, and push notifications work on real devices.

The PRD explicitly defines the MVP around this complete flow rather than feature depth. fileciteturn1file3L592-L618

# 2. Guiding Development Principles

Build the end-to-end critical path first; do not polish isolated screens before the core flow works.

Keep Supabase as the primary backend. Use Firebase only for Cloud Messaging, avoiding duplicate application data.

Keep the AI chatbot replaceable and independent from the core matching/chat workflow.

Enforce verification, cooldown, authorization and eligibility on the backend, not only in Flutter.

Use a shared Flutter component/style baseline so beginner contributors can build consistently.

Do not add deferred features simply because they are technically interesting.

Test every completed feature immediately instead of leaving integration and bug fixing until the final day.

These priorities directly address the PRD's identified risks: two beginner Flutter contributors, uncertain Alibaba Cloud AI availability, Firebase/Supabase integration complexity, and the tight six-day schedule. fileciteturn1file1L94-L152

# 3. Team Structure

| Person | Primary Ownership | Secondary Responsibility |
| --- | --- | --- |
| Usman — Team Lead | Architecture, Supabase/backend, matching, integration | Flutter review, shared components, QA, release |
| Habiba — UI/UX & Mobile | Flutter UI, seeker/donor flows, reusable widgets | UX testing and visual QA |
| Hassan — Mobile & Admin | Admin panel, Flutter support, verification UI | FCM/admin integration and testing |

The PRD identifies Usman as Team Lead, Habiba as UI/UX & Mobile, and Hassan as Mobile & Admin Panel. It also notes that two contributors are beginners, so work should be scoped narrowly and reviewed incrementally. fileciteturn1file0L11-L19

# 4. Priority System

| Priority | Meaning | Examples |
| --- | --- | --- |
| P0 — Critical | Must work for MVP/demo; blocks other work | Auth, DB, verification, matching, chat, FCM |
| P1 — Required | Required MVP behavior but can follow the critical path | Role switching, cooldown, admin flags, AI request helper |
| P2 — Polish | Improves quality but must not delay the core flow | Animations, advanced empty states, visual refinements |
| P3 — Deferred | Do not build for MVP | Payments, automated ID verification, ratings, hospital integration |

# 5. MVP Scope Lock

The MVP must include:

Email/phone authentication through Supabase Auth.

Single account with seeker/donor role switching.

Donor profile with blood group, city, health disclosure and hemoglobin fields.

Volunteer / Compensated for travel & time classification.

CNIC front + back and live selfie upload.

Manual admin approve/reject verification.

Automatic three-month donation cooldown.

City-level donor/request matching with blood-group filtering.

Role-specific map views.

Basic 1-to-1 text chat.

FCM push notifications for matches and messages.

Lightweight Alibaba Cloud AI chatbot for guided request creation.

Admin panel for verification and user/flag management.

Urgent and top-donor boolean flags.

These are the PRD's defined MVP implementations. fileciteturn1file7L592-L618

# 6. Explicitly Deferred

Payment gateway or in-app compensation.

Automated CNIC authenticity, face matching or biometric liveness.

Clinical validation of hemoglobin or health information.

Voice/video calling.

Blood-bank or hospital inventory integration.

Donor ratings/reviews.

Multi-language localization beyond the initial launch language.

Advanced automated donor ranking beyond city + blood-group filtering.

Seeker/donor web application; only the admin panel is web-based in MVP.

These are explicitly deferred by the PRD and should not enter the sprint unless all P0/P1 work is complete. fileciteturn1file2L217-L227

# 7. Dependency Map

Project setup
    ↓
Supabase + database schema
    ↓
Authentication + profile
    ↓
Donor verification + admin review
    ↓
Eligibility + cooldown
    ↓
Blood request + matching
    ↓
Maps
    ↓
Match initiation
    ↓
Chat
    ↓
FCM notifications
    ↓
AI request assistant
    ↓
Integrated QA → Demo build → Deployment

Important: AI is intentionally not on the critical path. The PRD specifies that the chatbot should be lightweight and replaceable if Alibaba Cloud tooling is delayed. fileciteturn1file1L96-L104

# 8. Phase 0 — Project Setup

Goal: eliminate setup uncertainty before feature development.

Create/confirm GitHub repository and branch strategy.

Create Flutter project and lock Flutter/Dart versions.

Create Supabase development project.

Create production Supabase project or reserve it for release.

Create Firebase project and configure Cloud Messaging.

Create Google Maps credentials/restrictions.

Confirm Alibaba Cloud AI tool/model and API access.

Create admin web project.

Create .env / secret management approach; never commit secrets.

Define development, staging/demo and production configurations.

Create README with setup instructions.

## Definition of Done — Setup

Every team member can clone the repositories and run the mobile app.

Flutter builds successfully on the target test devices.

Supabase connection works from development.

Firebase FCM test notification is received on at least one real device.

Admin dashboard runs locally.

All required environment variables are documented without exposing secrets.

# 9. Phase 1 — Database & Backend Foundation

Goal: create the data model and security foundation before UI depends on it.

Create profiles/users data structure.

Create donor profile fields.

Create blood requests.

Create matches.

Create conversations and messages.

Create verification records.

Create notifications and device token records.

Add status enums/constraints.

Add created_at/updated_at fields where needed.

Add indexes for blood group, city, availability, request status and conversation IDs.

Create RLS policies for user-owned data.

Create admin-only access paths.

## Backend Rules to Implement Early

A user can update only their own profile.

A donor cannot approve their own verification.

Verification status can only be changed through authorized admin logic.

Private CNIC/selfie files are never public.

Users can only access conversations in which they participate.

Suspended users cannot participate in matching/chat.

## Definition of Done — Backend Foundation

Schema can be recreated from migrations/scripts.

RLS is enabled on all user-facing tables.

Seed/test users can be created.

A basic authenticated CRUD operation works from Flutter.

Admin access is separated from normal user access.

# 10. Phase 2 — Authentication, Profiles & Roles

Goal: establish the identity and role system used by every subsequent feature.

Build sign-up/login.

Implement session persistence.

Create profile onboarding.

Implement seeker/donor role switch.

Collect blood group, city, donor classification and health fields.

Implement logout/session expiry handling.

Add validation and loading/error states.

## Definition of Done — Auth

A new user can register and log in.

Session survives app restart.

The same account can switch roles without creating another account.

Invalid credentials and network failures show useful errors.

Unauthorized screens cannot be accessed.

The PRD requires email/phone authentication and role switching through Supabase Auth. fileciteturn1file4L347-L355

# 11. Phase 3 — Donor Verification & Admin Panel

Goal: make verified donor discovery trustworthy enough for the MVP.

Build guided CNIC front upload.

Build CNIC back upload.

Build live selfie capture/upload.

Store files in private Supabase Storage buckets.

Create pending verification record.

Build admin verification queue.

Display submitted images securely to admin.

Implement approve/reject actions.

Implement rejection reason.

Allow rejected users to resubmit.

Notify donor when status changes.

Only approved donors become eligible for matching.

## Definition of Done — Verification

A donor can submit all three required images.

Admin sees the submission as pending.

Admin can approve or reject it.

Rejected users can resubmit.

Approved donor status is reflected in the app without reinstalling.

Sensitive files remain private.

The PRD requires manual CNIC/selfie verification and explicitly excludes automated ID/face matching from MVP. fileciteturn1file4L352-L355

# 12. Phase 4 — Eligibility & Donation Cooldown

Goal: prevent ineligible donors from appearing in active matching.

Add last_donation_date.

Implement three-month cooldown calculation server-side.

Create an eligibility condition used by matching queries.

Allow eligible donor to reappear automatically after cooldown.

Show donor's eligibility/availability state in their own profile.

Test dates around the exact three-month boundary.

## Definition of Done — Cooldown

A donor inside the cooldown is absent from matching results.

A donor whose cooldown has expired appears without admin action.

Changing the last donation date updates eligibility correctly.

Boundary-date tests pass.

The PRD specifically requires automatic three-month exclusion and automatic reappearance. fileciteturn1file4L356-L359

# 13. Phase 5 — Blood Requests & Matching

Goal: build the central Donora+ value proposition.

Create blood request form.

Collect blood group, city, urgency and notes.

Validate required fields.

Store active request.

Implement city-level filtering.

Implement blood-group compatibility/filtering.

Exclude unverified donors.

Exclude unavailable/suspended donors.

Exclude donors in cooldown.

Return eligible donors ordered by practical proximity or simple deterministic ordering.

Allow donor-side view of active requests matching their blood group.

Implement request lifecycle: active, matched/responded, completed, cancelled/expired.

## Definition of Done — Matching

A seeker can create an active request.

Only compatible, verified, eligible donors appear.

Donors outside the selected city are excluded.

An ineligible cooldown donor is excluded.

Donor can see relevant active requests.

No client-side-only eligibility bypass exists.

The MVP is intentionally limited to city-level matching and blood-group filtering rather than a complex ranking algorithm. fileciteturn1file7L603-L618

# 14. Phase 6 — Maps & Location

Goal: make matching visually actionable without exposing unnecessary private location data.

Request location permission only when needed.

Store city and appropriate coordinates.

Integrate Google Maps.

Create seeker map of compatible donors.

Create donor map of matching active requests.

Restrict results to the relevant city.

Use approximate/appropriate location presentation rather than exposing private residential coordinates.

Handle denied location permission gracefully.

## Definition of Done — Maps

Map loads on a real device.

Markers correspond to valid matching records.

Blood-group filtering updates the map.

City restriction works.

Location permission denial does not crash the app.

# 15. Phase 7 — Match Initiation & Chat

Goal: complete the core seeker-to-donor interaction.

Create match/contact record.

Prevent duplicate active matches for the same pair/request where appropriate.

Create conversation on match initiation.

Build 1-to-1 text chat UI.

Subscribe to Supabase Realtime messages.

Persist messages in PostgreSQL.

Implement sent/received states.

Implement basic read state if time allows.

Do not expose phone number automatically.

## Definition of Done — Chat

Seeker can initiate chat with a valid donor.

Donor can receive and reply.

Messages persist after app restart.

Realtime messages appear without manual refresh.

Users cannot read conversations they do not belong to.

The PRD defines the MVP communication layer as basic in-app 1-to-1 text chat. fileciteturn1file3L277-L285

# 16. Phase 8 — Firebase Cloud Messaging

Goal: make important events visible even when the app is not open.

Register FCM device token after authentication.

Store token in Supabase; do not duplicate user/application data in Firebase.

Implement server-side notification function.

Send match notification.

Send new message notification.

Send verification result notification.

Handle foreground notification.

Handle background/tap navigation.

Support token refresh.

## Definition of Done — Notifications

Notification reaches a real device within seconds under normal conditions.

Tapping notification opens the correct screen/context.

Expired/invalid tokens are handled.

No private medical or identity data is unnecessarily exposed in notification text.

The PRD explicitly scopes Firebase to Cloud Messaging and requires real-device notification testing. fileciteturn1file1L133-L143

# 17. Phase 9 — Alibaba Cloud AI Chatbot

Goal: add AI value without putting the core MVP at risk.

Confirm Alibaba Cloud AI/Qwen API and rate limits.

Create a secure Edge Function AI gateway.

Never expose AI API credentials in Flutter.

Define a narrow prompt for blood-request assistance.

Extract/suggest only structured request fields: blood group, city, urgency and notes.

Return structured data or clearly separated suggestions.

Let user review and confirm before submission.

Add basic failure/fallback state.

Keep chatbot independent from matching and chat.

## Definition of Done — AI

User can ask the assistant for help creating a request.

Assistant suggests request fields.

User remains in control and can edit values.

AI failure does not block manual request creation.

Secrets are server-side only.

The PRD requires the chatbot to assist with request creation and explicitly says its output should populate/suggest values rather than replace the request form. fileciteturn1file4L369-L371

# 18. Phase 10 — Admin Completion

Verification queue.

User search/list.

Approve/reject verification.

Edit core profile fields.

Suspend/activate account.

Toggle urgent-request flag.

Toggle top-donor flag.

Show request status.

Show basic audit information for important admin changes.

## Definition of Done — Admin

Admin can complete the full verification workflow.

Admin changes are reflected in the mobile app.

Admin-only actions are protected.

Suspended users cannot continue matching/chat actions.

The PRD acceptance criteria require verification review, flag management and profile editing with changes reflected without reinstalling the app. fileciteturn1file4L372-L375

# 19. Six-Day Hackathon Roadmap

The following schedule is intentionally aggressive because the PRD identifies a six-day build window. The order prioritizes the demonstrable end-to-end path and treats AI/polish as lower risk work. fileciteturn1file1L144-L152

| Day | Primary Goal | Usman | Habiba | Hassan | End-of-Day Gate |
| --- | --- | --- | --- | --- | --- |
| Day 1 | Setup + foundation | Repo, Supabase, schema, auth, RLS | Flutter setup, theme, auth/onboarding UI | Admin project setup, base screens | All environments run; auth works |
| Day 2 | Profiles + verification | Verification schema/storage/RLS | Donor profile + upload UI | Admin verification queue/review | Donor can submit; admin can review |
| Day 3 | Matching core | Eligibility, cooldown, matching queries | Seeker request + donor screens | Admin/user states + Flutter support | Verified eligible donor appears in matching |
| Day 4 | Maps + chat | Match APIs + Realtime | Maps + chat UI | Chat/admin integration | Seeker ↔ donor can chat |
| Day 5 | FCM + AI + integration | FCM/Edge Functions + AI gateway | Notification UX + AI UI | FCM/admin polish + integration QA | End-to-end flow works on real devices |
| Day 6 | QA + bug fixing + release | Critical bug fixes + release build | UI/UX QA + demo rehearsal | Admin QA + release support | Stable demo build; no P0 blockers |

# 20. Daily Development Rhythm

Start of day: 10-minute task sync and dependency check.

Work in small branches; merge completed slices rather than large unfinished branches.

Before merging: run analyzer/tests relevant to the changed feature.

After merging: one teammate performs a quick integration smoke test.

End of day: update task status, record blockers and prepare the next day's highest-priority tasks.

Do not wait until Day 6 to discover that two modules do not integrate.

# 21. Testing Strategy

## 21.1 Unit Tests

Three-month cooldown calculation.

Blood-group compatibility/filtering.

Request status transitions.

Role/permission checks where practical.

Validation of request payloads.

## 21.2 Widget/UI Tests

Login form validation.

Role switch.

Donor verification upload states.

Blood request form.

Chat message rendering.

Notification navigation.

## 21.3 Integration Tests

Auth → profile creation.

Donor → verification submission → admin approval.

Admin approval → donor appears in matching.

Cooldown → donor disappears from matching.

Request → match → chat.

Chat/message → FCM notification.

AI suggestion → request form.

## 21.4 Real-Device Tests

At least one Android physical device for FCM.

Camera/selfie capture.

Storage upload over mobile network.

Map rendering and permissions.

Background notification handling.

App restart/session persistence.

# 22. Mandatory End-to-End Demo Test

TEST SCENARIO

1. Register Donor A.
2. Complete donor profile.
3. Upload CNIC front/back + selfie.
4. Admin approves Donor A.
5. Set Donor A as available and eligible.
6. Register Seeker B.
7. Seeker B creates an urgent blood request.
8. Donor A appears on the matching map.
9. Seeker B initiates contact.
10. Donor A receives match notification.
11. Seeker B sends chat message.
12. Donor A receives message notification.
13. Donor A replies.
14. Verify realtime chat.
15. Change Donor A's last donation date to an ineligible date.
16. Refresh matching.
17. Confirm Donor A is excluded.
18. Restore eligible state and confirm reappearance.

This scenario directly validates the PRD's core demo metrics: request-to-chat flow, verification, real-device notifications and cooldown exclusion. fileciteturn1file5L449-L455

# 23. Bug-Fixing Process

| Severity | Definition | Action |
| --- | --- | --- |
| P0 | Crash, security issue, data leak, auth bypass, core demo flow blocked | Fix immediately; no release until resolved |
| P1 | Core feature broken but workaround exists | Fix before final demo |
| P2 | Minor functional/UI issue | Fix after P0/P1; may ship if low risk |
| P3 | Cosmetic/nice-to-have | Defer unless time remains |

Every bug report should contain:

Device/environment.

Steps to reproduce.

Expected result.

Actual result.

Screenshot/video if useful.

Severity.

Relevant logs/error message.

# 24. Security QA Checklist

No Supabase service-role key in Flutter.

No Alibaba Cloud API secret in Flutter.

Private CNIC/selfie storage cannot be accessed anonymously.

RLS is enabled and tested.

Users cannot edit another user's profile.

Users cannot access another user's private conversation.

Only admins can approve verification.

Suspended users cannot perform protected actions.

Push payloads do not contain unnecessary sensitive information.

Exact donor location is not unnecessarily exposed.

# 25. Performance & Reliability Checklist

Avoid unnecessary full-table queries.

Use pagination for lists.

Index frequently filtered fields.

Do not load all donor/request records into Flutter.

Show loading states for network operations.

Show retry states for failed network operations.

Prevent duplicate submissions with disabled buttons/idempotent backend operations.

Handle offline/poor-network conditions gracefully.

Dispose realtime subscriptions when screens are removed.

# 26. Deployment Plan

## 26.1 Development

Development Supabase project.

Debug Flutter build.

Test Firebase credentials.

Test admin locally.

## 26.2 Demo/Staging

Seed safe demo accounts.

Seed approved donor(s).

Seed a controlled blood request scenario.

Use real-device FCM.

Use production-like configuration without real sensitive personal data.

## 26.3 Production / Submission Build

Run final automated tests.

Run the mandatory end-to-end test.

Verify environment variables.

Verify Supabase RLS.

Verify private storage.

Verify FCM.

Build signed Android/iOS artifacts as applicable.

Deploy admin panel.

Tag the Git commit used for the final demo.

# 27. Release Gate

Do not call the MVP complete until all of the following are true:

Authentication works on a real device.

Role switching works.

Donor verification works end-to-end.

Admin approval/rejection works.

Cooldown is enforced automatically.

Seeker can create a request.

Compatible verified donors appear correctly.

Maps work.

Seeker and donor can chat.

FCM notification works on a real device.

AI assistant works or a clearly tested fallback preserves manual request creation.

Admin changes propagate to the app.

No P0 bugs remain.

No known critical security issue remains.

The full demo can be completed from clean test accounts without manual database manipulation during the presentation.

# 28. Definition of Done — Universal

A development task is considered Done only when:

The implementation satisfies its acceptance criteria.

The feature works from the actual UI, not only from a database/API test.

Loading, success and failure states are handled.

Authorization/security rules are enforced server-side where applicable.

Data persists correctly after app restart.

Relevant unit/widget/integration tests pass.

The feature has been tested on the target device/environment.

No new analyzer/build errors are introduced.

The branch is merged cleanly into the shared development branch.

The feature has been smoke-tested with at least one dependent feature.

The feature-specific acceptance criteria come from the PRD, including authentication/roles, verification, cooldown, matching/maps, chat/notifications, AI and admin behavior. fileciteturn1file4L347-L375

# 29. MVP Acceptance Matrix

| Feature | Acceptance Test | Priority | Dependency |
| --- | --- | --- | --- |
| Auth | User can sign up/login and persist session | P0 | Supabase |
| Roles | User switches seeker/donor on same account | P0 | Auth/Profile |
| Donor profile | Blood group, city, health fields saved | P0 | Profile |
| Verification | CNIC front/back + selfie → admin approve/reject | P0 | Storage/Admin |
| Cooldown | Ineligible donor excluded for 3 months | P0 | Donor profile |
| Blood request | Seeker creates active request | P0 | Auth/DB |
| Matching | Compatible verified eligible donor appears | P0 | Request/Cooldown |
| Maps | Donors/requests shown by city | P0 | Matching/Maps |
| Chat | Matched users exchange realtime text | P0 | Match/Realtime |
| FCM | Match/message notification arrives | P0 | Match/Chat + Firebase |
| AI assistant | Suggests request fields without blocking manual form | P1 | Alibaba AI |
| Admin | Review, flags, profile edits, suspend | P0 | Auth/DB/Storage |
| Urgent/top donor | Admin toggles boolean flags | P1 | Admin |

# 30. Final Roadmap Summary

SETUP
  ↓
DATABASE + RLS
  ↓
AUTH + ROLES
  ↓
DONOR PROFILE
  ↓
VERIFICATION + ADMIN
  ↓
COOLDOWN / ELIGIBILITY
  ↓
REQUESTS + MATCHING
  ↓
MAPS
  ↓
MATCH + CHAT
  ↓
FCM
  ↓
AI ASSISTANT
  ↓
INTEGRATED QA
  ↓
BUG FIXING
  ↓
RELEASE / DEMO

The recommended strategy is to reach a functioning seeker → matching → chat → notification flow as early as possible, then complete verification/admin and AI around it. This protects the project against the schedule and integration risks identified in the PRD while preserving the product's central value proposition.

# 31. Developer Starting Checklist

□ Clone repository and confirm Flutter/Dart version.

□ Create development .env/configuration.

□ Connect development Supabase project.

□ Create Firebase project and FCM configuration.

□ Create Google Maps credentials.

□ Confirm Alibaba Cloud AI access.

□ Create admin web project.

□ Apply database schema and RLS.

□ Implement auth.

□ Implement profile/role switching.

□ Implement donor verification.

□ Implement admin approval.

□ Implement cooldown.

□ Implement request creation.

□ Implement matching.

□ Implement maps.

□ Implement chat.

□ Implement FCM.

□ Implement AI request helper.

□ Run end-to-end demo test.

□ Fix P0/P1 issues.

□ Build final demo release.